## Checklist
TVA Ninja Cohort 3 – Agentic Workflow Workshop: Pre-Class Facilitator Checklist
Workshop date: Tuesday, Nov 3, 2026 · TVA Microsoft 365 GCC tenant · Facilitator: Wesley Floyd (Microsoft) – add co-facilitators · Microsoft facilitates; TVA participants build their own agents and flows
# | Phase | Category | Task | Owner | Due Date | Status | Notes / Evidence
1 | T-10 days | Tenant & Licensing | Confirm TVA Microsoft 365 GCC tenant name ({{TVA_TENANT_NAME}}) | TVA | 2026-10-26 | Not Started | Record exact tenant name/domain on the Placeholders sheet.
2 | T-10 days | Tenant & Licensing | Confirm a dedicated Copilot Studio environment in GCC — not the Default environment ({{TVA_COPILOT_STUDIO_ENVIRONMENT}}) | Joint | 2026-10-26 | Not Started | Capture environment name/URL; confirm participants have Environment Maker rights.
3 | T-10 days | Tenant & Licensing | Confirm Power Platform region for the environment ({{TVA_POWER_PLATFORM_REGION}}) | TVA | 2026-10-26 | Not Started | Record region shown in Power Platform admin center.
4 | T-10 days | Tenant & Licensing | Confirm Microsoft 365 Copilot licenses assigned to all participants | TVA | 2026-10-26 | Not Started | Attach roster with license status per participant.
5 | T-10 days | Tenant & Licensing | Confirm Copilot Studio access and capacity (messages/capacity allocated to the workshop environment) | Joint | 2026-10-26 | Not Started | Note capacity source (tenant/environment) and any limits.
6 | T-10 days | Tenant & Licensing | Confirm Power Automate premium needs — Copilot Studio agent actions called from flows | Joint | 2026-10-26 | Not Started | Identify who needs premium/per-user or per-flow coverage for the 3 flows.
7 | T-10 days | Governance & DLP | DLP policy review: place SharePoint, Approvals, Teams, Office 365 Outlook, Planner and Copilot Studio connectors in the same "Business" data group | TVA | 2026-10-26 | Not Started | Unclassified connectors are blocked at runtime — screenshot the policy scoped to the workshop environment.
8 | T-10 days | GCC Feature Parity | GCC parity check: Agent Builder is available in GCC, but embedded file content is NOT supported as a knowledge source in GCC — plan SharePoint knowledge instead | Microsoft | 2026-10-26 | Not Started | Confirm against current GCC service description; adjust labs if needed.
9 | T-10 days | GCC Feature Parity | Confirm in TVA's GCC tenant: generative answers over SharePoint knowledge, Copilot Studio agent actions from Power Automate, and publishing agents to Teams/M365 | Joint | 2026-10-26 | Not Started | Record pass/fail per capability; any gap becomes a lab workaround.
10 | T-10 days | Governance & DLP | Security/compliance sign-off that only public TVA content (plus customer-provided workshop content) is used | TVA | 2026-10-26 | Not Started | Name of approver + date; no internal/private data (e.g., Vantage, internal email/chat exports).
11 | T-7 days | Placeholders | Fill {{TVA_SHAREPOINT_SITE_URL}} — workshop SharePoint site URL | TVA | 2026-10-27 | Not Started | See Placeholders sheet.
12 | T-7 days | Placeholders | Fill {{TVA_KNOWLEDGE_LIBRARY_NAME}} (default: Knowledge-Public) | Joint | 2026-10-27 | Not Started | See Placeholders sheet.
13 | T-7 days | Placeholders | Fill {{TVA_TRANSMISSION_LIST_NAME}} (default: TransmissionProjects) | Joint | 2026-10-27 | Not Started | See Placeholders sheet.
14 | T-7 days | Placeholders | Fill {{TVA_TRANSMISSION_DRAFTS_LIST_NAME}} (default: TransmissionUpdateDrafts) | Joint | 2026-10-27 | Not Started | See Placeholders sheet.
15 | T-7 days | Placeholders | Fill {{TVA_PUBLICCOMMENTS_LIST_NAME}} (default: PublicComments) | Joint | 2026-10-27 | Not Started | See Placeholders sheet.
16 | T-7 days | Placeholders | Fill {{TVA_BRIEFREQUESTS_LIST_NAME}} (default: ExecutiveBriefRequests) | Joint | 2026-10-27 | Not Started | See Placeholders sheet.
17 | T-7 days | Placeholders | Fill {{TVA_ONEDRIVE_WORKSHOP_FOLDER}} (suggested: /TVANinjaCohort3/) | TVA | 2026-10-27 | Not Started | Subfolders: working-drafts/, demo-exports/.
18 | T-7 days | Placeholders | Fill {{TVA_SERVICE_AREA_REGION}} | TVA | 2026-10-27 | Not Started | Used to scope agent answers to TVA's service area.
19 | T-7 days | Placeholders | Fill {{TVA_TEAMS_WORKSHOP_TEAM}} — create/confirm the workshop Team | TVA | 2026-10-27 | Not Started | Team owner(s) recorded.
20 | T-7 days | Placeholders | Fill {{TVA_TEAMS_WORKSHOP_CHANNEL}} — create/confirm the workshop channel | TVA | 2026-10-27 | Not Started | Approved posts from all 3 flows land here.
21 | T-7 days | Placeholders | Fill {{TVA_APPROVER_GROUP_EMAIL}} — configure approver group | TVA | 2026-10-27 | Not Started | Mail-enabled group; confirm members can respond to Approvals.
22 | T-7 days | Placeholders | Fill {{TVA_DEFAULT_OWNER_TRANSMISSION}} — default Transmission owner | TVA | 2026-10-27 | Not Started | Name + email.
23 | T-7 days | Placeholders | Fill {{TVA_DEFAULT_OWNER_CAO}} — default CAO owner (Planner tasks from comment triage) | TVA | 2026-10-27 | Not Started | Name + email.
24 | T-7 days | Placeholders | Fill {{TVA_DEFAULT_OWNER_IT}} — default IT owner | TVA | 2026-10-27 | Not Started | Name + email.
25 | T-7 days | Placeholders | Fill {{FLOW_TRANSMISSION_UPDATE_APPROVAL_NAME}} (suggested: TVA-Transmission-Update-Approval) | Joint | 2026-10-27 | Not Started | Flow 1.
26 | T-7 days | Placeholders | Fill {{FLOW_PUBLICCOMMENT_TRIAGE_NAME}} (suggested: TVA-Public-Comment-Triage) | Joint | 2026-10-27 | Not Started | Flow 2.
27 | T-7 days | Placeholders | Fill {{FLOW_STRATEGIC_BRIEF_PUBLISH_NAME}} (suggested: TVA-Strategic-Brief-Publish) | Joint | 2026-10-27 | Not Started | Flow 3.
28 | T-7 days | Placeholders | Fill workshop settings: {{WORKSHOP_DATE}}, {{FACILITATOR_NAME}}, {{COHORT_NAME}} | Microsoft | 2026-10-27 | Not Started | Nov 3, 2026 · Wesley Floyd (Microsoft) + co-facilitators · TVA Ninja Cohort 3.
29 | T-7 days | Placeholders | Replace every placeholder across the workshop docs with confirmed values | Microsoft | 2026-10-27 | Not Started | Search docs for "{{" — zero remaining before T-5.
30 | T-5 days | SharePoint Setup | Confirm SharePoint site exists and participants have access ({{TVA_SHAREPOINT_SITE_URL}}) | TVA | 2026-10-29 | Not Started | Member/Edit permissions for all participants.
31 | T-5 days | SharePoint Setup | Create Knowledge-Public library with folders: Strategic-Plan, Transmission-Projects, Powerhouse-Stories, Reference-Policies, Generation | Joint | 2026-10-29 | Not Started | Folder names exactly as listed.
32 | T-5 days | SharePoint Setup | Create the 4 lists (TransmissionProjects, TransmissionUpdateDrafts, PublicComments, ExecutiveBriefRequests) using "TVA Cohort 3 - SharePoint List Import Kit.xlsx" | Joint | 2026-10-29 | Not Started | Column names must match docs/02 exactly.
33 | T-5 days | SharePoint Setup | Verify list columns incl. audit fields (FlowRunId, AgentVersion, Approver, ApprovalDecision, DecisionTimestamp, PublishedArtifactLink) on Drafts, PublicComments, ExecutiveBriefRequests | Microsoft | 2026-10-29 | Not Started | Spot-check against docs/02 column lists.
34 | T-5 days | SharePoint Setup | Restrict Stage columns to controlled values: Planning, Siting, Environmental Review, Survey/Realty, Construction, In Service, Needs human verification | Joint | 2026-10-29 | Not Started | Use a Choice column; no free text.
35 | T-5 days | SharePoint Setup | Load ≥5 transmission sample rows into TransmissionProjects (each with SourceUrl, Stage, PublicCommentStatus) | Joint | 2026-10-29 | Not Started | Data quality minimums per docs/02.
36 | T-5 days | Public Sources | Upload TVA FY26–FY30 Strategic Plan PDF to Strategic-Plan/ | Microsoft | 2026-10-29 | Not Started | Public tva.com source only.
37 | T-5 days | Public Sources | Upload transmission project pages to Transmission-Projects/ and Powerhouse stories to Powerhouse-Stories/ | Microsoft | 2026-10-29 | Not Started | Include SourceUrl for each item.
38 | T-5 days | Public Sources | Upload 2026 IRP executive summary (Generation/ or Reference-Policies/) | Microsoft | 2026-10-29 | Not Started | Public source; note page/section for citations.
39 | T-5 days | SharePoint Setup | Save a test file in the OneDrive workshop folder to confirm permissions | TVA | 2026-10-29 | Not Started | /TVANinjaCohort3/working-drafts/
40 | T-3 days | Agent Build & Test | Build and test Transmission Planning Navigator in facilitator environment | Microsoft | 2026-10-31 | Not Started | Project summary + stage/schedule prompts grounded in SharePoint.
41 | T-3 days | Agent Build & Test | Build and test Strategic Alignment Briefing Agent | Microsoft | 2026-10-31 | Not Started | Audience variants: Finance, Nuclear, CAO.
42 | T-3 days | Agent Build & Test | Build and test Transmission Comment Triage Agent | Microsoft | 2026-10-31 | Not Started | Category, urgency, NeedsHumanReview, draft response.
43 | T-3 days | Flow Build & Test | Pre-stage the 3 flows: Transmission Update Approval, Public Comment Triage, Strategic Brief Publish | Microsoft | 2026-10-31 | Not Started | Fallback for 45–50 min sessions: participants wire trigger/actions only.
44 | T-3 days | Flow Build & Test | Pre-create connections: SharePoint, Approvals, Teams, Office 365 Outlook, Planner, Copilot Studio | Joint | 2026-10-31 | Not Started | Connections in the workshop environment, allowed by DLP.
45 | T-3 days | Flow Build & Test | Dry-run approve AND reject branches on all 3 flows | Microsoft | 2026-10-31 | Not Started | Published / Needs Revision (Flows 1 & 3); Approved for Response / Revision Required (Flow 2).
46 | T-3 days | Flow Build & Test | Verify audit fields persist on list items after each run | Microsoft | 2026-10-31 | Not Started | FlowRunId, AgentVersion, Approver, ApprovalDecision, DecisionTimestamp, PublishedArtifactLink.
47 | T-3 days | Safety Tests | Safety test: missing data returns "Needs human verification" (no fabrication) | Microsoft | 2026-10-31 | Not Started | Screenshot response as evidence.
48 | T-3 days | Safety Tests | Safety test: out-of-scope request is refused | Microsoft | 2026-10-31 | Not Started | e.g., internal/private data request; screenshot refusal.
49 | T-1 day | Data Validation | Re-validate 5 sample rows vs tva.com: Claysville (In Service/Closed), Jones Chapel (Survey/Realty/Closed), Star Gap (Survey/Realty/Closed), Crossville (Siting/Open – comment period through Dec 3, 2026), Florence (Construction/Closed) | Microsoft | 2026-11-02 | Not Started | Note any changes from tva.com; update Stage/PublicCommentStatus.
50 | T-1 day | Data Validation | Update LastValidatedOn for all transmission rows | Microsoft | 2026-11-02 | Not Started | Set to validation date (Nov 2, 2026).
51 | T-1 day | Logistics | Confirm every participant can sign in to the GCC tenant, Copilot Studio and Power Automate | TVA | 2026-11-02 | Not Started | Track exceptions by name.
52 | T-1 day | Logistics | Room / Teams logistics: meeting link, room AV, screen sharing, Wi-Fi | Joint | 2026-11-02 | Not Started | Backup presenter laptop.
53 | T-1 day | Logistics | Load the interactive presenter package and test on the presenting device | Microsoft | 2026-11-02 | Not Started | Offline copy available.
54 | T-1 day | Logistics | Confirm breakout assignments: Transmission + Generation, Finance + Nuclear, IT + CAO | Joint | 2026-11-02 | Not Started | Share pair/group list with participants.
55 | Day of | Day-of Readiness | Environment check: sign in, open environment, run one agent prompt and one test flow | Microsoft | 2026-11-03 | Not Started | Before participants arrive.
56 | Day of | Day-of Readiness | Demo backups ready: screenshots of each agent and flow run | Microsoft | 2026-11-03 | Not Started | Use if live service is slow/unavailable.
57 | Day of | Day-of Readiness | Run timing plan per docs/11 (Context 5 · Transmission 12 · Briefing 10 · Comment triage + flow 10 · Q&A 8) | Microsoft | 2026-11-03 | Not Started | Hands-on mode: objective 5 · fill-in 5 · agent build 25–35 · flow 20–30 · debrief 10.
58 | Day of | Day-of Readiness | Confirm docs/00 fill-in template is open for participants | Microsoft | 2026-11-03 | Not Started | Participants complete in first 5 minutes.
59 | Post-workshop | Acceptance – Data & Governance | All source content is public TVA or customer-provided; no internal/private source references exist | Joint | 2026-11-10 | Not Started | Spot-check library and list SourceUrl values.
60 | Post-workshop | Acceptance – Data & Governance | All artifacts stored in SharePoint/OneDrive; outbound messages require approval | Joint | 2026-11-10 | Not Started | Verify approval step precedes every post/send.
61 | Post-workshop | Acceptance – Agent Quality | Agent responses include source-grounded language; missing data is flagged, not fabricated | Joint | 2026-11-10 | Not Started | Review sample transcripts.
62 | Post-workshop | Acceptance – Agent Quality | Transmission lifecycle explanation is accurate; role-based briefing adapts by work area | Joint | 2026-11-10 | Not Started | Check against controlled Stage values.
63 | Post-workshop | Acceptance – Workflow Quality | Approval branches work for approve/reject; SharePoint records persist complete audit fields | Joint | 2026-11-10 | Not Started | Run history + list item evidence.
64 | Post-workshop | Acceptance – Workflow Quality | Planner/Teams notifications route to expected owners; failed runs surface actionable errors | Joint | 2026-11-10 | Not Started | Test one deliberate failure.
65 | Post-workshop | Expansion Backlog | Follow up on expansion backlog: Nuclear outage comms, Dam-management seasonal ops, Finance rate-impact explainer, IT incident briefing, CAO hearing prep | Microsoft | 2026-11-10 | Not Started | Schedule follow-up session with work-area leads.

## Placeholders
Workshop Placeholders – values to confirm before class (docs/00 fill-in template)
Fill the TVA Value column by T-7 (Oct 27, 2026); defaults and suggestions come from docs/00 and docs/02.
Placeholder | Section | Description | Default / Suggested Value | TVA Value | Confirmed By
{{TVA_TENANT_NAME}} | Tenant and environment | TVA Microsoft 365 GCC tenant name | TVA to confirm
{{TVA_COPILOT_STUDIO_ENVIRONMENT}} | Tenant and environment | Copilot Studio / Power Platform environment for the workshop | Dedicated GCC environment (not Default)
{{TVA_POWER_PLATFORM_REGION}} | Tenant and environment | Power Platform region of the environment | TVA to confirm
{{TVA_SHAREPOINT_SITE_URL}} | SharePoint and OneDrive | Workshop SharePoint site URL | TVA to confirm
{{TVA_KNOWLEDGE_LIBRARY_NAME}} | SharePoint and OneDrive | Document library holding public knowledge sources | Knowledge-Public
{{TVA_TRANSMISSION_LIST_NAME}} | SharePoint and OneDrive | List of transmission projects | TransmissionProjects
{{TVA_TRANSMISSION_DRAFTS_LIST_NAME}} | SharePoint and OneDrive | List of transmission update drafts (Flow 1) | TransmissionUpdateDrafts
{{TVA_PUBLICCOMMENTS_LIST_NAME}} | SharePoint and OneDrive | List of public comments (Flow 2) | PublicComments
{{TVA_BRIEFREQUESTS_LIST_NAME}} | SharePoint and OneDrive | List of executive brief requests (Flow 3) | ExecutiveBriefRequests
{{TVA_ONEDRIVE_WORKSHOP_FOLDER}} | SharePoint and OneDrive | Personal OneDrive working folder | /TVANinjaCohort3/ (working-drafts/, demo-exports/)
{{TVA_SERVICE_AREA_REGION}} | SharePoint and OneDrive | TVA service-area region used to scope answers | TVA to confirm
{{TVA_TEAMS_WORKSHOP_TEAM}} | Teams and approvals | Microsoft Teams team for the workshop | TVA to confirm
{{TVA_TEAMS_WORKSHOP_CHANNEL}} | Teams and approvals | Teams channel where approved posts land | TVA to confirm
{{TVA_APPROVER_GROUP_EMAIL}} | Teams and approvals | Approver group email for all approval steps | TVA to confirm
{{TVA_DEFAULT_OWNER_TRANSMISSION}} | Teams and approvals | Default owner – Transmission | TVA to confirm
{{TVA_DEFAULT_OWNER_CAO}} | Teams and approvals | Default owner – CAO (Planner tasks from comment triage) | TVA to confirm
{{TVA_DEFAULT_OWNER_IT}} | Teams and approvals | Default owner – IT | TVA to confirm
{{FLOW_TRANSMISSION_UPDATE_APPROVAL_NAME}} | Power Automate flows | Flow 1 – transmission update draft approval | TVA-Transmission-Update-Approval
{{FLOW_PUBLICCOMMENT_TRIAGE_NAME}} | Power Automate flows | Flow 2 – public comment triage routing | TVA-Public-Comment-Triage
{{FLOW_STRATEGIC_BRIEF_PUBLISH_NAME}} | Power Automate flows | Flow 3 – strategic brief pack publisher | TVA-Strategic-Brief-Publish
{{WORKSHOP_DATE}} | Workshop settings | Workshop delivery date | Tuesday, Nov 3, 2026
{{FACILITATOR_NAME}} | Workshop settings | Facilitator(s) | Wesley Floyd (Microsoft) – add co-facilitators
{{COHORT_NAME}} | Workshop settings | Cohort name | TVA Ninja Cohort 3

## Summary
Readiness Summary – Status by Phase
Live counts from the Checklist sheet. % Complete = Done ÷ (Total − N/A).
Phase | Due Date | Not Started | In Progress | Done | Blocked | N/A | Total | % Complete
T-10 days | 2026-10-26 | 10 | 0 | 0 | 0 | 0 | 10 | 0%
T-7 days | 2026-10-27 | 19 | 0 | 0 | 0 | 0 | 19 | 0%
T-5 days | 2026-10-29 | 10 | 0 | 0 | 0 | 0 | 10 | 0%
T-3 days | 2026-10-31 | 9 | 0 | 0 | 0 | 0 | 9 | 0%
T-1 day | 2026-11-02 | 6 | 0 | 0 | 0 | 0 | 6 | 0%
Day of | 2026-11-03 | 4 | 0 | 0 | 0 | 0 | 4 | 0%
Post-workshop | 2026-11-10 | 7 | 0 | 0 | 0 | 0 | 7 | 0%
Total |  | 65 | 0 | 0 | 0 | 0 | 65 | 0%
Check: Summary total vs Checklist rows (should be 0) | [6 empty] | 0
Rows with blank or invalid Status (should be 0) | [6 empty] | 0
Formulas:
Due Date = MINIFS(Checklist!$F4:F200,Checklist!$B4:B200,[Phase])